CANChat ? Open WebUI Gap Analysis

How Far Behind

- **Commit gap:** `origin/main` has ~1,177 commits not in `upstream/main`; upstream has ~6,237 not

in CANChat. Divergence is substantial.

- **Diff surface:** Large churn across backend core (config/env, routers, models/migrations,

retrieval/vector stack, utils), frontend Svelte UI (`src` apps, admin/chat/layout/workspace), and

translations. Infra deltas are smaller (Docker/compose).

- **Merge test:** A trial merge surfaced conflicts in most backend files, many Svelte components,

i18n locales, lockfiles, and Dockerfile; CI workflows and LICENSE/README also conflicted.

CANChat Customizations (patterns from CANChat-only commits)

- **Core product / business logic (majority):**

- Retrieval improvements (async/hybrid search, weighted interleaving, concurrency settings).

- Metrics recording refinements (non-streaming responses, missing metric handling).

- Chat lifecycle tweaks (cleanup, preservation for pinned/archived, logging).

- Reasoning filter for title/tag generation.

- UX logic for metrics date validation and cleanup settings.

- **Config / infra:**

- Scheduler version/logging tweaks; occasional release bumps; minimal docker/compose drift.

- **Branding / copy / docs:**

- CHANGELOG/doc updates; translation wording tweaks (EN/FR and others).

- **Auth / security:** No standout CANChat-only auth/permission commits in the sampled set.

Recommended Migration Approach

1. **Prep:** Branch from `main`; re-fetch `upstream/main`; align toolchains (Node/Python) with

upstream; capture current env/secrets.

2. **Backend-first merge:** Reconcile in slices?config/env/constants ? routers/handlers ?

models/migrations ? retrieval/vector ? utils/storage. Apply upstream migrations in a test DB, then

reapply CANChat-specific migrations; plan data migration where schemas diverge.

3. **Frontend merge:** Align `src/lib/apis` with upstream API shape; then merge UI areas in batches

(chat/channel, admin, workspace, layout/shared components). Reconcile i18n by starting from upstream

locales and reapplying CANChat copy where needed.

4. **Infra/dep alignment:** Merge `Dockerfile`/compose and CI workflows; reintroduce CANChat

env/logging specifics; regenerate lockfiles (`package-lock`, `pyproject/uv`,

`backend/requirements*`).

5. **Branding/copy pass:** After code alignment, reapply CANChat branding, README/docs updates, and

translation tweaks.

6. **Validation:** Backend tests/migrations, frontend build/tests, E2E smoke (chat, retrieval,

admin), staging with prod-like data. Fix regressions, repeat as needed.

7. **Cutover:** Freeze changes, tag/release notes, deploy with rollback plan; monitor.

Effort Estimate (dev-weeks)

- **Lower:** 3?4 wks ? assumes clean reapplication of CANChat logic, minimal schema clashes, fast

conflict resolution, quick validation.

- **Realistic:** 6?8 wks ? substantial manual merges in backend retrieval/routers/models and

frontend Svelte, multiple test/fix cycles, some data migration work.

- **Upper:** 10?12+ wks ? if schema/data drift is large, E2E regressions pile up, or

compliance/review loops add rework; heavy branding/i18n reconciliation.

Key Risks

- **Schema/data drift:** Migrating DB/vector stores could cause data loss or downtime if not

rehearsed.

- **API/contract breaks:** Frontend API shape may differ; silent failures without thorough E2E.

- **Dependency/infra drift:** Docker/runtime/lockfile mismatches could break builds or runtime

stability.

- **Feature regressions:** High-touch areas (chat lifecycle, retrieval/hybrid search, metrics) are

fragile.

- **i18n/branding churn:** Thousands of locale lines; risk of overwriting CANChat-specific copy.